## Schedule
NST Interview Prep Portal — 75-Day Delivery Plan (5 people)
Project start (Day 1) | 2026-06-11
Launch (Day 75) | 2026-08-24
Team | PL · UX · FE · BE · QA
Phase / Task | Owner | Role | Start day | End day | Duration (days) | Start date | End date | Dependency / notes
1 · Requirement gathering & docs
Stakeholder workshops | PL | Project Lead | 1 | 6 | 6 | 2026-06-11 | 2026-06-16 | Kickoff & elicitation
SRS / requirement spec doc | PL | Project Lead | 4 | 10 | 7 | 2026-06-14 | 2026-06-20 | Signed-off requirements
Personas & journey maps | UX | UI/UX Designer | 5 | 10 | 6 | 2026-06-15 | 2026-06-20 | All 3 portals
Architecture & data model | BE | Backend / Data | 6 | 10 | 5 | 2026-06-16 | 2026-06-20 | Locks schema — unlocks scraping track
2 · UI/UX design & sign-offs
Student Portal wireframes | UX | UI/UX Designer | 11 | 15 | 5 | 2026-06-21 | 2026-06-25
Faculty Portal wireframes | UX | UI/UX Designer | 14 | 18 | 5 | 2026-06-24 | 2026-06-28
Admin Portal wireframes | UX | UI/UX Designer | 17 | 21 | 5 | 2026-06-27 | 2026-07-01
Hi-fi mockups & design system | UX | UI/UX Designer | 15 | 22 | 8 | 2026-06-25 | 2026-07-02
Faculty sign-off | PL | Project Lead | 21 | 22 | 2 | 2026-07-01 | 2026-07-02 | GATE — faculty design review
Product team sign-off | PL | Project Lead | 23 | 24 | 2 | 2026-07-03 | 2026-07-04 | GATE — unlocks development
3 · Portal development (dummy data)
Student backend (dummy data) | BE | Backend / Data | 25 | 32 | 8 | 2026-07-05 | 2026-07-12 | After product sign-off
Student frontend build | FE | Frontend | 27 | 36 | 10 | 2026-07-07 | 2026-07-16 | Needs student APIs
Student integration & review | FE | Frontend | 35 | 38 | 4 | 2026-07-15 | 2026-07-18
Faculty backend APIs | BE | Backend / Data | 37 | 43 | 7 | 2026-07-17 | 2026-07-23
Faculty frontend build | FE | Frontend | 38 | 46 | 9 | 2026-07-18 | 2026-07-26
Faculty integration & review | FE | Frontend | 45 | 48 | 4 | 2026-07-25 | 2026-07-28
Admin backend APIs | BE | Backend / Data | 44 | 50 | 7 | 2026-07-24 | 2026-07-30
Admin frontend build | FE | Frontend | 48 | 54 | 7 | 2026-07-28 | 2026-08-03
Admin integration & review | FE | Frontend | 53 | 58 | 6 | 2026-08-02 | 2026-08-07 | All 3 portals built on dummy data
4 · Data scraping & pipeline (parallel)
Source discovery & ToS review | PL | Project Lead | 13 | 20 | 8 | 2026-06-23 | 2026-06-30 | Starts once data model is locked
Build scrapers (priority set) | BE | Backend / Data | 20 | 40 | 21 | 2026-06-30 | 2026-07-20 | CAPACITY RISK — BE also on backends
Scraper infra & orchestration | FE | Frontend | 24 | 38 | 15 | 2026-07-04 | 2026-07-18 | CAPACITY RISK — FE also on frontends
Raw extraction & JSON dumps | BE | Backend / Data | 38 | 48 | 11 | 2026-07-18 | 2026-07-28 | 35+ sources → raw JSON
Data cleaning & normalization | QA | QA / Testing | 42 | 52 | 11 | 2026-07-22 | 2026-08-01 | Dedup, encoding, company names
Claude API classification | BE | Backend / Data | 48 | 58 | 11 | 2026-07-28 | 2026-08-07 | Tag topic / difficulty / round
Syllabus mapping & gap dataset | PL | Project Lead | 52 | 60 | 9 | 2026-08-01 | 2026-08-09 | Feeds faculty gap analysis
5 · Integration, testing & launch
Real data integration | FE | Frontend | 58 | 64 | 7 | 2026-08-07 | 2026-08-13 | Replace dummy data in all portals
System & end-to-end testing | QA | QA / Testing | 60 | 67 | 8 | 2026-08-09 | 2026-08-16
Performance & load testing | QA | QA / Testing | 66 | 70 | 5 | 2026-08-15 | 2026-08-19
Security testing & UAT | QA | QA / Testing | 69 | 73 | 5 | 2026-08-18 | 2026-08-22
Bug fixes & regression | BE | Backend / Data | 62 | 74 | 13 | 2026-08-11 | 2026-08-23
Final launch & go-live | ALL | Whole team | 75 | 75 | 1 | 2026-08-24 | 2026-08-24 | MILESTONE — launch day
Formulas:
Start date = B2+[Start day]-1
End date = B2+[End day]-1

## Gantt
NST Interview Prep Portal — Visual Timeline (Day 1 = 11 Jun 2026)
|  | 11 Jun |  |  |  | 15 Jun |  |  |  |  | 20 Jun |  |  |  |  | 25 Jun |  |  |  |  | 30 Jun |  |  |  |  | 5 Jul |  |  |  |  | 10 Jul |  |  |  |  | 15 Jul |  |  |  |  | 20 Jul |  |  |  |  | 25 Jul |  |  |  |  | 30 Jul |  |  |  |  | 4 Aug |  |  |  |  | 9 Aug |  |  |  |  | 14 Aug |  |  |  |  | 19 Aug |  |  |  |  | 24 Aug
Task | Own | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75
1 · Requirement gathering & docs
Stakeholder workshops | PL
SRS / requirement spec doc | PL
Personas & journey maps | UX
Architecture & data model | BE
2 · UI/UX design & sign-offs
Student Portal wireframes | UX
Faculty Portal wireframes | UX
Admin Portal wireframes | UX
Hi-fi mockups & design system | UX
Faculty sign-off | PL
Product team sign-off | PL
3 · Portal development (dummy data)
Student backend (dummy data) | BE
Student frontend build | FE
Student integration & review | FE
Faculty backend APIs | BE
Faculty frontend build | FE
Faculty integration & review | FE
Admin backend APIs | BE
Admin frontend build | FE
Admin integration & review | FE
4 · Data scraping & pipeline (parallel)
Source discovery & ToS review | PL
Build scrapers (priority set) | BE
Scraper infra & orchestration | FE
Raw extraction & JSON dumps | BE
Data cleaning & normalization | QA
Claude API classification | BE
Syllabus mapping & gap dataset | PL
5 · Integration, testing & launch
Real data integration | FE
System & end-to-end testing | QA
Performance & load testing | QA
Security testing & UAT | QA
Bug fixes & regression | BE
Final launch & go-live | ALL | [74 empty] | ◆
Legend
PL — Project Lead
UX — UI/UX Designer
FE — Frontend
BE — Backend / Data
QA — QA / Testing
ALL — Whole team